## Sheet1
COSC1076 ¦ Semester 1 2020
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name: | frAgile Engineers |  | Progress Classes: | Ahead
Group Member: | Sara Imamura |  |  | On-track
Group Member: | Kee Chew Huang |  |  | Behind
Group Member: | Sanjay Sajeesh |  |  | Way Behind
Tutor: | Dale & Tim
Class: | Thurs 2:30
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | Sara Imamura | Kee Chew Huang | Sanjay Sajeesh
|  |  | Group Formed -Done |  | Weekly Contribution | Discussion on ADTs | Created GitHub Repo, Discussion on ADTs | Created Teams Page, Discussion on ADTs
|  |  | MS Team created-Done |  | Issues
|  |  | Git Repo created-Done |  | Other Notes
Basic Main menu with "credits"-Done
Choice of where to use linked list, vector & array- Done
|  | Progress | Ahead
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Sara Imamura | Kee Chew Huang | Sanjay Sajeesh
|  |  | Initial Design of ADTs (classes and potential methods)- Done |  | Weekly Contribution | Implementation of ADTs | Implementation of ADTs,Menu | Implementation of ADTs
|  |  | Main menu- Done |  | Issues
|  |  | User Prompt (for gameplay), but no/minimal error checking- Done |  | Other Notes
Linked List implementation- Done
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required- Done
ADT implementation for storing information, game loop logic not required-Done
|  | Progress | On-track
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) | Behind | Weekly Contribution | implementation of factory property | implementation of game engine | implementation of players (mosaic) data structure
|  |  | Initialisation of data strctures for new game | On-track | Issues | incompatibility with tilebag ADT | incompatibility with tilebag ADT | incompatibility in tile bag ADT and mosaic data structure
|  |  | Write Tests Cases for common uses | Way Behind | Other Notes
|  |  | Gameplay for single round, that is selecting and moving of tiles from a factory to players mosaic | Way Behind
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | A | B | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | adding test mode and test cases, report writing, error checking of user prompt, debugging of known errors and file handling | scoring and automated placement of mosaic, modification in player's data structures, debugging of known errors and file handling | file handling, mosaic implementation, debugging of known errors,comments and modification of ADTs
|  |  | Full error checking of user prompt |  | Issues
|  |  | Automated placement of tiles at end of round, but no scoring |  | Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind